## SIT
Business process | Tester name | Status | Add/view documents | Relationship | Tested On | Test data | Comments | Other Testers | Other Testers | Other Testers
Events | Shubham Balaji Suryawanshi | Passed | Passed | NA | 19th Nov | Event - Spain Broker Events |  | Dheeraj Gurbani | Shubham Balaji Suryawanshi | Haribabu
Broker registration | Shubham Balaji Suryawanshi | Passed | Passed | NA | 20th Nov | BR-29647 | 19/11: Tile issue 20/11: Fixed and tested | Dheeraj Gurbani | Shubham Balaji Suryawanshi | Haribabu
Document validator | Shubham Balaji Suryawanshi | Passed | Passed | NA | 19th Nov | V-0004 |  | Dheeraj Gurbani | Shubham Balaji Suryawanshi | Haribabu
BR document history | Shubham Balaji Suryawanshi | Passed | Passed |  | 19th Nov | BRH-43865 |  | Dheeraj Gurbani | Shubham Balaji Suryawanshi | Haribabu
Broker ledger | Shubham Balaji Suryawanshi | Passed | Passed | NA | 19th Nov | BL-10002 |  | Dheeraj Gurbani | Shubham Balaji Suryawanshi | Haribabu
Mortgage | Mohammad Furkan Asif Momin | NA | NA | NA | 20th Nov |  | 20/11: profile access issue where email of Furkan was different in AD and salesforce. 20/11: Issue fixed and tested. Furkan comments: Is not being used. | Mohammad Furkan Asif Momin
Advance payment rebates | Mohammad Furkan Asif Momin | Passed | Passed | Passed | 20th Nov | A-2124 |  | Mohammad Furkan Asif Momin
demand | Mohammad Furkan Asif Momin | Passed | Passed | NA | 20th Nov | D199949 |  | Mohammad Furkan Asif Momin
receipt | Mohammad Furkan Asif Momin | Passed | Passed | Passed | 20th nov | R513178 |  | Mohammad Furkan Asif Momin
payment request | Mohammad Furkan Asif Momin | Passed | Passed | Passed | 20th Nov | PR-0266430 | New requirement : Establish relationship with Booking. | Mohammad Furkan Asif Momin
Business process | Shubham Balaji Suryawanshi Mohammad Furkan Asif Momin | Passed | Passed | NA | 19th Nov | BP-0007169 | New requirement :1. Add Mortgage, refund, reallocation as a document type classification & Folders in the BP New requirement :2. Based on users profile, they should not be selecting several document types. Payment Completion Certificate , Refund Process, Re Allocation Process, Mortgage Process. this all should be avaibale in Business Process for collection porfile to upload only | CRM - Shiva and Furkan | Sales - Dheeraj, Naryana and Nikhil
Booking | Shubham Balaji Suryawanshi Mohammad Furkan Asif Momin | Passed | Passed | Passed | 19th Nov | B-35495 |  | Narayana | Prince

## UAT Plan
Business process | Teams 1 | Teams 2 | Team 3 | Team 4
Events | Channel Ops |  |  |  | Dheeraj Gurbani | Shubham Balaji Suryawanshi |  | CRM | Sapna Jha and Kavya | Sapphire | Payment request, booking process and booking
Broker registration | Channel Ops |  |  |  | Dheeraj Gurbani | Shubham Balaji Suryawanshi |  | Collections | Akkad and Mathhews | Sapphire | Advance payment rebates, demand, reciept, payment request
Document validator | Channel Ops |  |  |  | Dheeraj Gurbani | Shubham Balaji Suryawanshi |  | Registration + DLD | Sherif Hassan | Sapphire
BR document history | Channel Ops |  |  |  | Dheeraj Gurbani | Shubham Balaji Suryawanshi |  | Sales Operation | Ganesh Prasad | Hartland 1 | Booking, Receipts and PR
Broker ledger | Channel Ops |  |  |  | Dheeraj Gurbani | Shubham Balaji Suryawanshi |  | Digital Marketing | Dinav Dileep, Nikhil Augustine | Hartland 1 | Not using any of these
Mortgage |  |  |  |  | Mohammad Furkan Asif Momin |  |  | Marketing | Mary Gonzales and Shawn Aaron Dalmeida | Hartland 1 | Not using any of these
Advance payment rebates |  | Collections |  |  | Mohammad Furkan Asif Momin |  |  | Facility management/CAFM | Asmita Jaiswal + Syed Deepthi Menon shawn michael lopez + Jacquline | Hartland 1 | Not using any of these
demand |  | Collections |  |  | Mohammad Furkan Asif Momin |  |  | Sobha community management | Swapna varma | Hartland 1
receipt |  | Collections | Sales operation | Resistration/DLD | Mohammad Furkan Asif Momin
payment request | CRM | Collections | Sales operation |  | Mohammad Furkan Asif Momin
Business process | CRM |  |  | Resistration/DLD | CRM - Shiva and Furkan | Sales - Dheeraj, Naryana and Nikhil
Booking | CRM |  | Sales operation | Resistration/DLD | Narayana | Prince
CRM | Sara taha with Sunny | Payment request, booking process and booking | 2025-11-26 11:00 |  | IRISH room | UAT | Completed | Signed
Collections | Akkad and Mathhews | Advance payment rebates, demand, reciept, payment request | 45987.625 |  | Online | UAT | Completed | Sent doc for sign
Registration + DLD | Sherif Hassan | reciept, Booking and busienss process. | On leave |  |  |  | Completed | Signed
Sales Operation | Ganesh Prasad | Booking, Receipts and PR | 2025-11-27 11:30 |  | Online | UAT | Completed | Signed
Channel Ops |  | Events, broker registration, document validator, Br doc history and broker ledger. | 2025-11-27 12:00 |  | Online | Demo
| Business Team | Comments
| Sapna Jha | email pending
| Kapil shah | user not there
| Akkad | user not there
| Sherif Hassan | done
| Ganesh Prasad | done
| Sonal Sehgal | email pending
| Kavya Pramod | email pending
| Mathhews | done

## UAT
Business process | Testing team | Tester name | Open BW | Add/view documents | Relationship | Tested On | Test data | Comments
Events | Channel Ops |  |  |  | NA
Broker registration | Channel Ops |  |  |  | NA
Document validator |  |  |  |  | NA
BR document history | Channel Ops
Broker ledger | Channel Ops |  |  |  | NA
Advance payment rebates | Collections | Akkad Singalaxana
Demand | Collections | Akkad Singalaxana |  |  | NA
Receipt | Collections | Akkad Singalaxana
Receipt | Sales Ops | Ganesh prasad | Passed | Passed | Passed | 2025-11-27 | R-60230
Receipt | Registration/DLD | Sherif Hassan | Passed | Passed | Passed | 2025-12-16 | R-372187
Payment request | CRM | Sara taha | Passed | Passed |  | 2025-11-26 | PR-0000020
Payment request | Collections | Akkad Singalaxana |  |  |  | 2025-12-05 | PR-0088982
Payment request | Sales Ops | Ganesh Prasad | Passed | Passed | Passed | 2025-11-27 | PR-0000369
Business process | CRM | Sara taha | Passed | Passed | NA | 2025-12-04 | BP-0000544 | 26-Nov: SFDC categories should be non editable. <4-Dec: Resolved> 4-Dec: Add Pre-registration document folder in the BP Business object. < 4: Dec : Fixed and tested.> 4-Dec: A report to showcase the documents notifying the expiry date. <4-Dec: We will accomodate this report in the phase 2 of the project>
Business process | Registration/DLD | Sherif Hassan | Passed | Passed | NA | 2025-12-16 | BP-0002049 | Add busienss process type & Current Business process Step name.
Booking | CRM | Sara taha | Passed | Passed | Passed | 2025-11-26 | B-35495 | 26-Nov: Date of expiry attribute feasibility. <Fixed and tested on 4th Dec. OTPS to add a new column for the documents to add the expiry column.> 26-Nov: Resale business object to be developed < 4: Dec : Under development and will be delivered in hypercare support.>
Booking | Sales Ops | Ganesh Prasad | Passed | Passed | Passed | 2025-11-27 | B-10650
Booking | Registration/DLD | Sherif Hassan | Passed | Passed | Passed | 2025-12-16 | B-11009